## Slide 1: 4. REQUIREMENTS Management Ch.07 Requirements management practices & Accommodating Changes
Software requirement engineering (Undergraduate)

## Slide 2: Accommodating New or changed requirements
Requirements management is the process of documenting, analyzing, tracing, prioritizing and agreeing on requirements and then controlling change and communicating to relevant stakeholders. It is a continuous process throughout a project.
Slide-2

## Slide 3: Accommodating New or changed requirements
Requirements Baseline is a set of requirements that stakeholders have agreed to, often defining the contents of a specific planned release or development iteration.
A baseline is a software configuration management concept that helps you to control change without seriously impeding justifiable requirements change.
For example, the elements of a requirements model have been documented and reviewed. Errors are found and corrected. Once all parts of the model have been reviewed, corrected, and then approved, the requirements model becomes a baseline.
Slide-3

## Slide 4: Requirements management process
Slide-4

## Slide 5: Accommodating New or changed requirements
By deferring lower-priority requirements to later iterations or cutting them completely
By obtaining additional staff or outsourcing some of the work
By extending the delivery schedule or adding iterations to an agile project
By sacrificing quality to ship by the original date
Slide-5

## Slide 6: Requirement attributes
Date the requirement was created
Current version number of the requirement
Author who wrote the requirement
Priority
Origin or source of the requirement
Rationale behind the requirement
Release number or iteration to which the requirement is allocated
Stakeholder to contact with questions or to make decisions about proposed changes
Validation method to be used or acceptance criteria (soft satisfaction)
Slide-6

## Slide 7: Tracking requirements status
Slide-7

## Slide 8: Resolving requirements issues
Some of the benefits of using an issue-tracking tool are:
  Issues from multiple requirements reviews are collected so that no issue ever gets lost.
  The project manager can easily see the current status of all issues.
  A single owner can be assigned to each issue.
  The history of discussion around an issue can be retained (continue to have).
  The team can begin development earlier with a known set of open issues rather than having to wait until the SRS is complete.
Slide-8

## Slide 9: Resolving requirements issues
Slide-9

## Slide 10: Why manage changes?
An organization that’s serious about managing its software projects must ensure that:
  Proposed requirements changes are thoughtfully evaluated before being committed to.
  Appropriate individuals make informed business decisions about requested changes.
  Change activity is made visible to affected stakeholders.
  Approved changes are communicated to all affected participants.
Slide-10

## Slide 11: Managing scope creep
The most effective technique for controlling scope creep is the ability to say “no”.
People don’t like to say “no,“ and development teams can receive intense pressure to always say “yes.“
Philosophies such as “the customer is always right” or “we will achieve total customer satisfaction” are fine in the abstract, but you pay a price for them.
Ignoring the price doesn’t alter the fact that change is not free.
The president of one software tool vendor is familiarized to hearing the development manager say “not now” when he suggests a new feature.
  “Not now” is more appealing than a simple rejection. It holds the promise of including the feature in a subsequent release.
Slide-11

## Slide 12: Change control policy
All changes must follow the process. If a change request is not submitted in accordance with this process, it will not be considered.
No design or implementation work other than feasibility exploration will be performed on unapproved changes.
Simply requesting a change does not guarantee that it will be made. The project’s change control board (CCB) will decide which changes to implement.
The contents of the change database must be visible to all project stakeholders.
Impact analysis must be performed for every change.
Every incorporated change must be traceable to an approved change request.
The rationale behind every approval or rejection of a change request must be recorded.
Slide-12

## Slide 13: A change control process description
Slide-13

## Slide 14: The change control board - CCB
CCB composition: The CCB membership should represent all groups who need to participate in making decisions within the scope of that CCB’s authority. Consider selecting representatives from the following areas:
    Project or program management
    Business analysis or product management
    Development
    Testing or quality assurance
    Marketing, the business for which the application is being built, or customer representatives
    Technical support or help desk
Slide-14

## Slide 15: CCB – Making Decisions
Each CCB needs to define its decision-making process, which should indicate:
  The number of CCB members or the key roles that constitute a decision-making quorum (required number)
  The decision rules to be used.
  Whether the CCB Chair can overrule the CCB’s collective decision.
  Whether a higher level of CCB or management must ratify (approve) the group’s decision.
Slide-15

## Slide 16: Change control tools
To support your change process, look for a tool that:
  Allows you to define the attributes that constitute a change request.
  Allows you to implement a change request life cycle with multiple change request statuses.
  Enforces the state-transition model so that only authorized users can make specific status changes.
  Records the date of each status change and the identity of the person who made it.
  Provides customizable, automatic email notification when an Originator submits a new request or when a request’s status is updated.
  Produces both standard and custom reports and charts.
Slide-16

## Slide 17: Measuring change activity
Consider tracking the following aspects of your requirements change activity:
  The total number of change requests received, currently open, and closed
  The number of added, deleted, and modified requirements
  The number of requests that originated from each change origin (e.g. customer, marketing)
  The number of changes received against each requirement since it was baselined
  The total effort devoted to processing and implementing change requests
Slide-17

## Slide 18: Measuring change activity (CNTD.)
Slide-18

## Slide 19: Change impact analysis
Impact analysis procedure
  Understand the possible implications of making the change. A requirement change often produces a large ripple (wave) effect, leading to modifications in other requirements, architectures, designs, code, and tests. Changes can lead to conflicts with other requirements or can compromise quality attributes, such as performance or security.
  Identify all the requirements, files, models, and documents that might have to be modified if the team incorporates the requested change.
  Identify the tasks required to implement the change, and estimate the effort needed to complete those tasks.
Slide-19

## Slide 20: Change impact analysis
Slide-20

## Slide 21: Change impact analysis
Slide-21

## Slide 22: Change impact analysis
Slide-22

## Slide 23: Change impact analysis
Following is a simple procedure for evaluating the impact of a proposed requirement change:
  Work through the checklist in Figure 28-5.
  Work through the checklist in Figure 28-6. Some requirements management tools include an impact analysis report that follows traceability links and finds the system elements that depend on the requirements affected by a change request.
  Use the worksheet in Figure 28-7 to estimate the effort required for the anticipated tasks. Most change requests will require only a portion of the tasks on the worksheet.
  Sum the effort estimates.
  Identify the sequence in which the tasks must be performed and how they can be interleaved with currently planned tasks.
  Estimate the impact of the proposed change on the project’s schedule and cost.
  Evaluate the change’s priority compared to other pending requirements.
  Report the impact analysis results to the CCB.
Slide-23

## Slide 24: Impact analysis template
Slide-24

## Slide 25: Change management on agile projects
Slide-25

## Slide 26: references
Wiegers, K., & Beatty, J. (2013). Software requirements. Pearson Education
Slide-26